## Sheet1
Front End UPOD Testing
Description | Location | Priority | Date Found | Found By | Status | Date Resolved | Resolved By | Notes
Box width of Moderator and Administrator email list extends past the screen frame | adminView.html | Medium | 2017-12-20 | Abel Worku
Moderator list box and Administrator list box not aligned with each other | adminView.html | Medium | 2017-12-20 | Abel Worku
Clicking on a section in the left sidebar retrieves the section, but does not include the elements at the start of that particular edit section, such as the "Section Title" input box and the blue header with the Section name | edit.html | Low | 2017-12-20 | Abel Worku
Add "List of Administrator Emails" to the Administrator list box, for consistency with the Moderator list box's initial text | adminView.html | Low | 2017-12-20 | Abel Worku
The sidebar button "Add Section" should have a little more spacing between it and the following section name for the sections list | edit.html | Low | 2017-12-20 | Abel Worku
The "move up" arrow and "move down" arrow appear to transport its corresponding section past a "one-up" or "one-down" action, after subsequent clicks | edit.html | Low | 2017-12-20 | Abel Worku
Section names in the sidebar appear not to follow its corresponding "move up" or "move down" action from the arrows, occurring after multiple successive clicks | edit.html | Low | 2017-12-20 | Abel Worku
Moderator emails list box does not have an identifying title of "Moderator List" | adminView.html | Medium | 2017-12-20 | Abel Worku
The arrow button to search ended up below the search bar on the right side | home.html | Low | 2017-12-20 | Xavier Kuttamparambil